## Slide 1
Exercise 4 – Waterfall
Read carefully the document ”Descrição projeto.docx," which describes the information system to be implemented to support the operations of a distribution and beverage company. This specification resulted from the Analysis and Requirements Gathering and the ongoing Design & Architecture phase.
Putting yourself in the role of the project manager of the technology consulting company that was awarded the project, elaborate on the project plan for the remaining phases of the project, aligned with the waterfall methodology:
Identify the technical profiles (resources) needed for implementation. Assign an hourly cost to each profile (ask in case of doubt), assuming that the resources will be hired on an outsourcing basis at the usual market value.
Build the WBS (tasks, estimates, dependencies).
Identify the Critical Path.
What is the total estimated cost of the project, at least for the labor component?